## Detailed Job Costing
DETAILED JOB COSTING BY PROJECT (SAMPLE)
Cost-code level detail (Procore budget buckets / QBO accounts) with estimate vs actual and margin impact.
Procore Project ID | Project | Union / Trade | Cost Code | Cost Category (Budget Line) | Estimated Budget | Actual Cost to Date (QBO) | Variance $ | Variance % | Committed (Open) | Forecast at Completion | Margin Impact Notes
PR-24017 | Suffolk County HS – Gym Addition | Carpenters Local 290 | 01-1000 | General Conditions | 62000 | 68500 | 6500 | 10.48% | 940 | 69440 | Site access constraints
PR-24017 | Suffolk County HS – Gym Addition | Carpenters Local 290 | 02-2100 | Union Labor – Wages | 420000 | 455000 | 35000 | 8.333% | 15400 | 470400 | Overtime due to schedule compression
PR-24017 | Suffolk County HS – Gym Addition | Carpenters Local 290 | 02-2200 | Union Dues & Fringe Benefits | 185000 | 198000 | 13000 | 7.027% | 9200 | 207200 | Benefit rate increase
PR-24017 | Suffolk County HS – Gym Addition | Carpenters Local 290 | 03-3100 | Materials | 260000 | 245000 | -15000 | -5.769% | 31200 | 276200 | Vendor discount / buyout savings
PR-24017 | Suffolk County HS – Gym Addition | Carpenters Local 290 | 04-4100 | Subcontractors | 120000 | 135000 | 15000 | 12.5% | 0 | 135000 | Scope creep / added prep
PR-24017 | Suffolk County HS – Gym Addition | Carpenters Local 290 | 05-5100 | Workers Comp & GL | 68000 | 82000 | 14000 | 20.59% | 0 | 82000 | Payroll exceeded policy estimate
PR-24022 | Town Hall Interior Renovation | Drywall Finishers Local 197 | 01-1000 | General Conditions | 22000 | 21200 | -800 | -3.636% | 2640 | 23840 | Lean site staffing
PR-24022 | Town Hall Interior Renovation | Drywall Finishers Local 197 | 02-2100 | Union Labor – Wages | 145000 | 138000 | -7000 | -4.828% | 17400 | 155400 | Improved crew efficiency
PR-24022 | Town Hall Interior Renovation | Drywall Finishers Local 197 | 02-2200 | Union Dues & Fringe Benefits | 64000 | 61000 | -3000 | -4.688% | 7680 | 68680 | Accurate estimating
PR-24022 | Town Hall Interior Renovation | Drywall Finishers Local 197 | 03-3100 | Materials | 105000 | 98000 | -7000 | -6.667% | 12600 | 110600 | Buyout savings
PR-24022 | Town Hall Interior Renovation | Drywall Finishers Local 197 | 04-4100 | Subcontractors | 45000 | 41000 | -4000 | -8.889% | 5400 | 46400 | Scope aligned
PR-24022 | Town Hall Interior Renovation | Drywall Finishers Local 197 | 05-5100 | Workers Comp & GL | 25000 | 24000 | -1000 | -4% | 3000 | 27000 | Within policy estimate
PR-24031 | Hospital Wing Fit-Out (Private) | Electricians Local 25 | 01-1000 | General Conditions | 48000 | 52000 | 4000 | 8.333% | 1760 | 53760 | Extended night work coordination
PR-24031 | Hospital Wing Fit-Out (Private) | Electricians Local 25 | 02-2100 | Union Labor – Wages | 285000 | 272000 | -13000 | -4.561% | 34200 | 306200 | Productivity above plan
PR-24031 | Hospital Wing Fit-Out (Private) | Electricians Local 25 | 02-2200 | Union Dues & Fringe Benefits | 124000 | 118000 | -6000 | -4.839% | 14880 | 132880 | Dues aligned
PR-24031 | Hospital Wing Fit-Out (Private) | Electricians Local 25 | 03-3100 | Materials | 210000 | 225000 | 15000 | 7.143% | 10200 | 235200 | Material price escalation
PR-24031 | Hospital Wing Fit-Out (Private) | Electricians Local 25 | 04-4100 | Subcontractors | 95000 | 88000 | -7000 | -7.368% | 11400 | 99400 | Scope transfer to in-house
PR-24031 | Hospital Wing Fit-Out (Private) | Electricians Local 25 | 05-5100 | Workers Comp & GL | 38000 | 41000 | 3000 | 7.895% | 1560 | 42560 | Classification adjustment
PR-24044 | Fire District Admin Building | Laborers Local 66 | 01-1000 | General Conditions | 18000 | 19500 | 1500 | 8.333% | 660 | 20160 | Mobilization add-ons
PR-24044 | Fire District Admin Building | Laborers Local 66 | 02-2100 | Union Labor – Wages | 99000 | 101500 | 2500 | 2.525% | 9380 | 110880 | Weather impacts
PR-24044 | Fire District Admin Building | Laborers Local 66 | 02-2200 | Union Dues & Fringe Benefits | 44000 | 45000 | 1000 | 2.273% | 4280 | 49280 | Standard
PR-24044 | Fire District Admin Building | Laborers Local 66 | 03-3100 | Materials | 76000 | 73000 | -3000 | -3.947% | 9120 | 82120 | Material substitutions
PR-24044 | Fire District Admin Building | Laborers Local 66 | 04-4100 | Subcontractors | 28000 | 26000 | -2000 | -7.143% | 3360 | 29360 | Scope reduced
PR-24044 | Fire District Admin Building | Laborers Local 66 | 05-5100 | Workers Comp & GL | 19000 | 20000 | 1000 | 5.263% | 1280 | 21280 | Slight overage
PR-24053 | Library Modernization | Painters Local 1231 | 01-1000 | General Conditions | 20000 | 19000 | -1000 | -5% | 2400 | 21400 | Efficient scheduling
PR-24053 | Library Modernization | Painters Local 1231 | 02-2100 | Union Labor – Wages | 118000 | 112000 | -6000 | -5.085% | 14160 | 126160 | Crew mix optimization
PR-24053 | Library Modernization | Painters Local 1231 | 02-2200 | Union Dues & Fringe Benefits | 51000 | 48500 | -2500 | -4.902% | 6120 | 54620 | Standard
PR-24053 | Library Modernization | Painters Local 1231 | 03-3100 | Materials | 92000 | 88500 | -3500 | -3.804% | 11040 | 99540 | Buyout
PR-24053 | Library Modernization | Painters Local 1231 | 04-4100 | Subcontractors | 41000 | 39500 | -1500 | -3.659% | 4920 | 44420 | Scope aligned
PR-24053 | Library Modernization | Painters Local 1231 | 05-5100 | Workers Comp & GL | 22000 | 21500 | -500 | -2.273% | 2640 | 24140 | Within estimate

## Executive Summary
EXECUTIVE JOB PROFITABILITY SUMMARY (MULTI-PROJECT)
Portfolio view by project, aligned to QBO Customer/Job + Class and Procore Budget/Commitments.
Procore Project ID | Project (QBO Customer:Job) | Owner / Client | Union / Trade | PM | Revised Contract (Incl. COs) | Costs to Date (Actual) | Committed Costs (Open POs/Subs) | Estimate to Complete (ETC) | Forecast Cost at Completion (EAC) | Forecast Gross Profit | GP % | Cash Margin (Billed - Costs) | Status | Billed to Date | Over / (Under) Billing | Retainage Held | Backlog Remaining (Rev) | Remaining Cost (EAC - Cost to Date) | Backlog GP % | WIP / Billing Risk Flag
PR-24017 | Suffolk County HS – Gym Addition | Suffolk County | Carpenters Local 290 | J. Rivera | 1325000 | 1085000 | 165000 | 210000 | 1295000 | 30000 | 2.264% | -35000 | Critical | 1050000 | -35000 | 95000 | 275000 | 210000 | 1.976% | High
PR-24022 | Town Hall Interior Renovation | Town of Brookhaven | Drywall Finishers Local 197 | A. Patel | 445000 | 352000 | 54000 | 60000 | 412000 | 33000 | 7.416% | 28000 | Critical | 380000 | 28000 | 42000 | 65000 | 60000 | 10.61% | Low
PR-24031 | Hospital Wing Fit-Out (Private) | Stony Brook Partner | Electricians Local 25 | M. Chen | 910000 | 598000 | 210000 | 185000 | 783000 | 127000 | 13.96% | 42000 | Review | 640000 | 42000 | 64000 | 270000 | 185000 | 16.13% | Low
PR-24044 | Fire District Admin Building | Fire District | Laborers Local 66 | S. Gomez | 335000 | 245000 | 58000 | 65000 | 310000 | 25000 | 7.463% | 45000 | Critical | 290000 | 45000 | 31000 | 45000 | 65000 | 14.93% | Low
PR-24053 | Library Modernization | Town of Islip | Painters Local 1231 | K. O'Brien | 395000 | 255000 | 72000 | 78000 | 333000 | 62000 | 15.7% | 50000 | On Track | 305000 | 50000 | 30500 | 90000 | 78000 | 24.42% | Low
PORTFOLIO CFO METRICS (SAMPLE)
Working Capital | 450000
Current Ratio | 1.55
Quick Ratio | 1.12
Cash as % of Monthly Payroll | 85%
Equity | 820000
Debt-to-Equity Ratio | 1.1
Net Over/(Under) Billings | 130000

## Billing & WIP
BILLING, WIP & CASH FLOW SNAPSHOT
Billing vs costs, retainage, and WIP-style over/under positions (municipal + private).
Procore Project ID | Project | Owner / Client | Revised Contract | Billed to Date | Costs to Date | Over / (Under) Billing | Retainage Held | Net Billings (Less Retainage) | Cash Margin (Billed - Costs) | Pct Billed | Pct Costed | Billing Risk | Recommended Action
PR-24017 | Suffolk County HS – Gym Addition | Suffolk County | 1325000 | 1050000 | 1085000 | -35000 | 95000 | 955000 | -35000 | 79.25% | 81.89% | High | Immediate billing & scope review
PR-24022 | Town Hall Interior Renovation | Town of Brookhaven | 445000 | 380000 | 352000 | 28000 | 42000 | 338000 | 28000 | 85.39% | 79.1% | Low | Maintain billing cadence
PR-24031 | Hospital Wing Fit-Out (Private) | Stony Brook Partner | 910000 | 640000 | 598000 | 42000 | 64000 | 576000 | 42000 | 70.33% | 65.71% | Low | Maintain billing cadence
PR-24044 | Fire District Admin Building | Fire District | 335000 | 290000 | 245000 | 45000 | 31000 | 259000 | 45000 | 86.57% | 73.13% | Low | Maintain billing cadence
PR-24053 | Library Modernization | Town of Islip | 395000 | 305000 | 255000 | 50000 | 30500 | 274500 | 50000 | 77.22% | 64.56% | Low | Maintain billing cadence

## Profit Fade & Risk Monitor
PROJECT RISK & PROFIT FADE MONITOR (SAMPLE)
Early-warning indicators for margin erosion, underbilling exposure, retainage drag, and change order risk.
Procore Project ID | Project | Original Bid GP % (Assumed) | Current Forecast GP % | Margin Decline (pp) | Underbilling Exposure | Retainage % of Contract | Aging Change Orders (Days) | Risk Flag | Recommended Focus
PR-24017 | Suffolk County HS – Gym Addition | 8% | 2.264% | -5.736% | 35000 | 7.17% | 65 | High | Immediate WIP, billing & CTC review
PR-24022 | Town Hall Interior Renovation | 10% | 7.416% | -2.584% | 0 | 9.438% | 65 | High | Immediate WIP, billing & CTC review
PR-24031 | Hospital Wing Fit-Out (Private) | 15% | 13.96% | -1.044% | 0 | 7.033% | 35 | Low | Maintain cadence
PR-24044 | Fire District Admin Building | 9% | 7.463% | -1.537% | 0 | 9.254% | 65 | High | Immediate WIP, billing & CTC review
PR-24053 | Library Modernization | 10% | 15.7% | 5.696% | 0 | 7.722% | 20 | Low | Maintain cadence

## Bonding & Banking Dashboard
SURETY & BANKING CONFIDENCE DASHBOARD (SAMPLE)
Key indicators sureties and lenders typically review for mid-market contractors.
Metric | Value | Why It Matters
Working Capital | 450000 | Supports bonding capacity and absorbs project cash cycle volatility.
Current Ratio | 1.55 | Measures short-term liquidity; low ratios can constrain growth.
Quick Ratio | 1.12 | More conservative liquidity measure excluding less-liquid current assets.
Equity | 820000 | A primary driver of surety confidence and capacity.
Debt-to-Equity | 1.1 | Higher leverage can reduce bonding flexibility.
Net Over/(Under) Billings | 130000 | Large underbillings may indicate billing/CO issues; overbillings may inflate cash temporarily.
Largest Single Job Exposure (% of Contract) | 34% | Concentration risk increases surety scrutiny.
Cash Flow Coverage Ratio (EBITDA / Debt Service) | 1.35 | Ability to service debt; lenders often look for > 1.25x.
Equipment Debt Ratio (Equip Debt / Total Debt) | 0.42 | Shows how much leverage is tied to equipment financing.

## Backlog & Cash Flow Forecast
BACKLOG-TO-CASH FORECAST (SAMPLE)
Forecast revenue, gross profit, payroll and net cash position over the next 6 months based on remaining backlog.
Month | Projected Revenue | Projected Gross Profit | Projected Cash Inflow | Projected Payroll | Net Cash Position
Apr 2026 | 89400 | 7262.1114 | 82248 | 24459.5316 | 407788.4684
May 2026 | 119200 | 9682.8152 | 109664 | 32612.7088 | 484839.7595
Jun 2026 | 134100 | 10893.1672 | 123372 | 36689.2974 | 571522.4621
Jul 2026 | 134100 | 10893.1672 | 123372 | 36689.2974 | 658205.1647
Aug 2026 | 134100 | 10893.1672 | 123372 | 36689.2974 | 744887.8672
Sep 2026 | 134100 | 10893.1672 | 123372 | 36689.2974 | 831570.5698

## Labor Efficiency & Margin
LABOR EFFICIENCY & MARGIN PERFORMANCE (SAMPLE)
Labor productivity and margin indicators by project—useful for union and merit-shop operations.
Procore Project ID | Project | Union / Trade | Revised Contract | Field Headcount (Avg) | Revenue per Field Employee | Labor Wages | Avg Loaded Rate | Estimated Labor Hours | Actual Labor Hours | Labor Hours Variance % | Labor % of Revenue
PR-24017 | Suffolk County HS – Gym Addition | Carpenters Local 290 | 1325000 | 12 | 110416.6667 | 455000 | 62 | 7338.7097 | 7925.8065 | 8% | 55.47%
PR-24022 | Town Hall Interior Renovation | Drywall Finishers Local 197 | 445000 | 6 | 74166.6667 | 138000 | 55 | 2509.0909 | 2709.8182 | 8% | 50.11%
PR-24031 | Hospital Wing Fit-Out (Private) | Electricians Local 25 | 910000 | 8 | 113750 | 272000 | 72 | 3777.7778 | 3891.1111 | 3% | 47.36%
PR-24044 | Fire District Admin Building | Laborers Local 66 | 335000 | 5 | 67000 | 101500 | 50 | 2030 | 2192.4 | 8% | 49.7%
PR-24053 | Library Modernization | Painters Local 1231 | 395000 | 12 | 32916.6667 | 112000 | 62 | 1806.4516 | 1806.4516 | 0% | 46.08%

## Insurance Labor Quota
CROSS-PROJECT LABOR & BURDEN ANALYSIS (HIGH-VALUE)
Labor, union dues/fringes, and insurance burden compared to targets—built for bid accuracy & margin control.
Procore Project ID | Project | Union / Trade | Revised Contract | Labor Wages | Union Dues & Fringe | Workers Comp & GL | Total Labor Burden (All-In) | All-In Labor % of Revenue | Insurance % of Payroll | Target All-In Labor % | Target Insurance % | Variance to Target (pp) | Risk Flag | Avg Loaded Hourly Rate (Assumed) | Estimated Direct Labor Hours | Labor Productivity (Rev / Labor $)
PR-24017 | Suffolk County HS – Gym Addition | Carpenters Local 290 | 1325000 | 455000 | 198000 | 82000 | 735000 | 55.47% | 18.02% | 36% | 5.5% | 19.47% | High | 62 | 7338.7097 | 2.9121
PR-24022 | Town Hall Interior Renovation | Drywall Finishers Local 197 | 445000 | 138000 | 61000 | 24000 | 223000 | 50.11% | 17.39% | 34% | 5.5% | 16.11% | High | 55 | 2509.0909 | 3.2246
PR-24031 | Hospital Wing Fit-Out (Private) | Electricians Local 25 | 910000 | 272000 | 118000 | 41000 | 431000 | 47.36% | 15.07% | 36% | 5.5% | 11.36% | High | 72 | 3777.7778 | 3.3456
PR-24044 | Fire District Admin Building | Laborers Local 66 | 335000 | 101500 | 45000 | 20000 | 166500 | 49.7% | 19.7% | 36% | 5.5% | 13.7% | High | 50 | 2030 | 3.3005
PR-24053 | Library Modernization | Painters Local 1231 | 395000 | 112000 | 48500 | 21500 | 182000 | 46.08% | 19.2% | 36% | 5.5% | 10.08% | High | 62 | 1806.4516 | 3.5268